## Slide 1
Project Management
Delivering Value Through Projects

## Slide 2: Why Project Management?
“You don’t see yourself being a project manager, so why take this course?”
Develops different types of critical thinking skills.
Most careers will have you engage in project work.
You ask better questions as a project stakeholder.
You understand where to look for signs of problems.
You know what to expect when engaged in project work.
“Not many projects are to send someone into space, so we start small and work our way up the complexity ladder.”

## Slide 3
“It Depends”
The most used answer in project management

## Slide 4: Course Review
Course Outline
13 Sections, 60-90 Minutes Each
Team Case Study
  Short & Progressive Presentations
Referencing the Project Management Body of Knowledge(PMBOK®) 6th and 7th Editions
Slides are Background for Conversations
Sections
Introduction to Project Management
Waterfall(Standard) vs. Agile
Project Initiation
Project Planning
Resource/People Management
Communications Management
Scope Management
Schedule/Time Management
Cost Management
Risk Management
Project Transition
Strategic Implementations
Project Mgt. Careers & Tool Chest Review

## Slide 5: Team Project
New Project Management Application
Implementation
Teams of 3-5
Short Presentations
Progressive Content
Plan for a Minium Viable Product
Build a Pipeline of Added Value

## Slide 6: Introduction to Project Management
What is Project Management and Why is it Important?
Section 1

## Slide 7: What is Project Management?
Definitions: Project, Project Management, and Program Management
Temporary: There is a definable beginning and end
Unique: Creation of something new (Product, Service, Capability)
Changes: Takes something existing and adds additional value
Progressive: Broken down into steps and methodically implemented
Application of knowledge, skills, tools & techniques used in the execution of projects and programs
Integrating different teams, resources, and organizations
Herding the cats and pulling-off the wedding
Integrated projects that are dependent on each other
Projects that may not be connected but drive a higher-level strategy
Application of project, program, and portfolio management skills
Section 1

## Slide 8: Portfolio Management
Grouping of Projects & Programs Under Single Owner
Individual Projects or Programs of Multiple Projects.
Representing Strategic Projects, Customer Projects, Continuous Improvement Projects, etc.
Supporting Resources can be Direct Reporting or Matrix
Prioritization of Projects, Programs, and Resources.
Status Reporting of Projects, Programs, and Portfolio.
Leadership & Development of Project Managers.
Monitoring and Controlling the Implementation of Portfolio Projects & Programs.
REPORT
Portfolio
MGT
PRIORITIZE
EXECUTE
CONTROL
VALIDATE
Section 1

## Slide 9: Portfolio Structure
Portfolio Structure isn’t a Leadership Structure
Owner 1
Owner 2
Owner 3
Owner 4
Owner 5
Strategic Portfolio
Sub-Portfolio or Domain 1
Sub-Portfolio or Domain 2
Projects & Programs
Resources
Budgets & Measurements
Domain 1a
Projects & Programs
Resources
Budgets & Measurements
Domain 1b
Projects & Programs
Resources
Budgets & Measurements
Domain 1c
Projects & Programs
Resources
Budgets & Measurements
Sub-Portfolio or Domain 3
Domain 3a
Projects & Programs
Resources
Budgets & Measurements
Domain 3b
Projects & Programs
Resources
Budgets & Measurements
Domain Examples
Human Resources
Technology
  Hardware
  Software
  Security
Operations
Finance
  Payroll
  Tax
Note: Every Organization Structures Domains and Resources Differently
Section 1

## Slide 10: Why Project Management?
Project Management Helps
  Deliver objectives
  Meet expectations
  Increase chances of success
  Resolve problems & issues
  Respond to risks more timely
  Optimize resources
  Manage constraints
  Manage change
Tendencies of Projects Not Managed
  Missed deadlines
  Cost overruns
  Poor fitness of use
  Rework
  Uncontrolled scope
  Loss of organization reputation
  Unsatisfied stakeholders
Projects Deliver Value, Solve Problems, and Create Opportunities
Section 1

## Slide 11: Attributes of a Project Manager
SKILLS
Project Management
Facilitation
Leadership
Communications
Analytics
Team Building
Attributes
Attention to Details
Active Listening
Curiosity
Seeks Input
Pragmatic & Methodical
Sets an Example
“The project manager isn’t the smartest person in the room in all areas, but being a generalist sure helps.”
Section 1

## Slide 12: Blending Skills and Experiences
Project Management
Leadership
Industry Knowledge
Section 1

## Slide 13: Leadership Powers
Formal
Power Based on Position
Reward
Giving Incentives/Rewards
Penalty
Able to Penalize Team
Expert
Subject Matter Expertise
Referent
Referencing Higher Positions
Section 1

## Slide 14: Project Success
What Defines Success?
SCOPE
COST
SCHEDULE
VALUE
Section 1

## Slide 15: Tripple Constraints
They are Real
Section 1
Scope Drives
Cost + Time
Budget Drives
Time + Scope
Time Drives
Scope + Budgets
Impacts to Fitness of Use
Time + Scope + Budget

## Slide 16: Organizationally Deep Strategy, Culture, Mission, Vision, & Values
Highest-Level Organizational Strategy
Highest-Level Mission, Vision, and Values
Business Units / Regional Area Strategy
Mission, Vision, and Values
Functional Area Strategy
Mission, Vision, and Values
Personal Strategy
Mission, Vision, and Values
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Highest
Lowest
Alignment
Section 1

## Slide 17: Project Management Areas of Focus
Knowledge, Skills, and Experience
Knowledge Areas
Project Life Cycle
Starting
Organizing/Plan
Doing the Work / Implementation
Ending
Process Groups
Initiation
Planning
Executing
Monitor & Control
Closing
Integration
Scope
Schedule
Cost
Quality
Resource
Communications
Risk
Procurement
Stakeholder
Key:
Gate / Milestone
Project Phase
Potential Use
Timeline
Section 1
PMBOK® 6th Edition
7th Edition Changed
6th Still Relevant

## Slide 18: Two Methodologies with Different Approach's
Standard/Waterfall Project or Agile
Section 1
Standard Project Method
Starts from Nothing
Delivers a Minimum Viable Product (MVP)
Clearly Defined Objectives
Experienced Resources
Longer Durations
Larger Project Teams
Dispersed Resources (Possible Time Zones)
Agile Method
Agile comes from Lean Methodologies
Minimum Viable Product (MVP) Exists
Short Iterations to Deliver Value
A Pipeline of Ideas Ready to Go
  User Stories
Smaller Consistently Changing Teams
Teams Closer, if not Collocated
Hybrid

## Slide 19: Complexity
Understanding It and Accounting For It
Section 1
Technology
Geography
Organizations
Goals/Objectives
Skilled Positions
The List Goes On, and On
???????
Understanding complexity is understanding how many people are needed to support.
People represent functions, skills, locations, languages, etc.
Lower Complexity
Higher Complexity
People Deliver Projects

## Slide 20: Information Flow
Strategy, Desired Outcomes, Deliverables, and Progress
Senior Leadership
Portfolios
Programs and Projects
Operations
Strategy
Desired Outcomes, Benefits, & Value
Deliverables with Support & Maintenance Information
Information for Updates, Fixes, & Adjustments
Performance Information & Progress
Portfolio Performance Information
Outcomes, Benefits, Value Performance Analysis
PMI® PMBOK® 7th Edition “A System for Value Delivery”
Section 1

## Slide 21: Project Management Tools
Lower Complexity Projects
Cloud Based Application
≈ $500 - $1,200 for 5 Seats, Annually
Lower Complexity Projects
Cloud Based Application
≈ $250 per User, Annually
Mid-High Complexity Projects
Desktop Application / Central is Cloud Based
≈ $500 One-Time Licensing Fee per User
Lower Complexity Projects
Cloud Based Application
≈ $7 - $19 per User, per Month
Low to Medium Complexity Projects
Cloud Based Application
≈ $110 - $230 per User, Annually
Tool Complexity

## Slide 22: Project Management Professional (PMP®)
Requirements
  High school diploma or GED
    60 Months/5 Years Experience within Past 8 Years
  ≥ 4 Year Degree
    36 Months/3 Years Experience within Past 8 Years
  ≥35 hours of project management education/training
  60 Professional Development Units (PDU) every three years
Certification Exam
  180 Questions in 3:50 Hours
  Price: $425 PMI Member/$675 nonmembers
PMP Stats
  Average U.S. Median Salary ≈ $120k
  Current Holders ≈ 1.5m Worldwide
    >500,000 in North America (November 2024)
  Top Countries: U.S., Canada, China
Section 1

## Slide 23: Project Management Body of Knowledge (PMBOK®) Guide 7th Edition
The Standard for Project Management
  A System for Value Delivery
  Project Management Principles
Project Performance Domains
  Stakeholder Performance
  Team Performance
  Development Approach & Lifecycle Performance
  Planning Performance
  Project Work Performance
  Planning Performance
  Measurement Performance
  Uncertainty Performance
Tailoring
Models, Methods, and Artifacts
The Project Management Institute (PMI®)
PMBOK® Guide 7th Edition
7th Edition Radically Changed from Previous Editions
Section 1
“Shift to a Principle-based standard, focused on intended outcomes rather than deliverables.”

## Slide 24: Certified Associate in Project Management (CAPM®)
Requirements
  High school diploma or GED
  No experience requirements
  ≥23 hours of project management education/training
  15 Professional Development Units (PDU) every three years
Certification Exam
  150 Questions in 3:00 Hours
  Price: $225 PMI Member/$300 nonmembers
CAPM Stats
Average U.S. Median Salary ≈ $72k
Current Holders ≈ 1.7m Worldwide
Types of Positions
  Assistant Project Manager
  Project Administrator
  Project Analyst
  Project Coordinator
  Project Manager
  Technical Project Manager
Section 1

## Slide 25: Other Project Management Credentials
https://www.pmi.org
https://www.prince2.com
Section 1
Program Management Professional (PgMP®)
Portfolio Management Professional (PfMP®)
PMI Professional in Business Analysis (PMI-PBA®)
PMI Risk Management Professional (PMI-RMP®)
PMI Scheduling Professional (PMI-SP®)
Prince2 Foundation
Prince2 Practitioner
Prince2 Agile Foundation
Prince2 Agile Practitioner
PMI Agile Certified Practitioner (PMI-ACP®)
Disciplined Agile Scrum Master (DASM®)
Disciplined Agile Senior Scrum Master (DASSM®)
Undergraduate, Graduate, or University Certifications/Degrees

## Slide 26: Team Exercise: Getting the Band Together
Start Forming Teams & Prepare for Introductions
Team Organization
Separate into Teams
Preferably Different Skills
Pick an Application
Team Exercise

## Slide 27: Standard Approach vs. Agile
Two Methods with Different Structures
Which to Use & Why Both are Needed
Section 2

## Slide 28: Two Methodologies with Different Approaches
Standard/Waterfall Project or Agile
Section 2
Standard Project Method
Starts from Nothing
Delivers a Minimum Viable Product (MVP)
Clearly Defined Objectives
Experienced Resources
Longer Durations
Larger Project Teams
Dispersed Resources (Possible Time Zones)
Predictable
Agile Method
Agile comes from Lean Methodologies
Minimum Viable Product (MVP) Exists
Short Iterations to Deliver Value
A Pipeline of Ideas Ready to Go
  User Stories
Smaller Consistently Changing Teams
Teams Closer, if not Collocated
Adaptive
Hybrid
Centralized Structure
Decentralized Structure

## Slide 29: Minimum Viable Product (MVP)
Delivering Initial Value
Foundational Project Deliverables
Decreases Time to Initial Delivery
Solves Immediate Needs/Problem
Includes Multiple Integrated Pieces
Established Base Solution
Stakeholders Evaluate Performance
Identify Future Needs/Value Iterations
Prioritize Needs, and Short-Term Sequence
Allocate Resources for Adaptive Approach
Section 2

## Slide 30: Regular, Standard, Waterfall Project Management
Section 2
Ideation / Commercial Notification
Knowledge Gap
Project Team Engagement
1st Level Cost Estimates, Schedule, Scope, Resourcing, Risk
Project Approved & kick-off Sessions
Time
Ideation & Approvals
Initiation & Planning
Requirements / Discovery / Revised Cost / Updated Timelines
Acceptance of Baseline Schedule, Cost, Scope, Risk, Etc.
Design/ Develop / Test / Train
Scope, Schedule, Cost Controls
Solution Design / Core Development / Unit Testing
User Acceptance Testing, End User Training
Integration & End-to-End Testing / Training Data Setup
Go-Live Support / Hypercare
Steady State
Transition to
Run the Business
Support
Close
Lifecycle
Predictive Approach

## Slide 31: Standard Team Structure Example
Different Projects = Different Resources
Section 2
Centralized
Core Business
Project Manager(s)
PROJECT
External Org.
Sponsor(s)
Project Manager
Integration Lead(s)
Application Lead(s)
Hardware Lead(s)
Tech Security Lead(s)
Legal Lead
Finance Lead
Compliance Lead
Technology Project Manager
Operations Lead
Human Resource Lead
Marketing Lead

## Slide 32: What is Value?
User Experience
Market Expansion
Cost Reduction
Quality Gains
What does an incremental gain do in these areas?
What other categories define value?
Section 2
“Something of worth, importance, or usefulness.”

## Slide 33: Adaptive/Agile Structure
Different Value Iterations = Different Resources
ARCHITECT
Ensures the Capability is Built Right
PROJECT LEAD
Coordinates the Capability Build
TEAM MEMBERS
Builds the Capability
OWNER
Ensures the Right Capability is Built
STAKEHOLDERS
SPECIALISTS
Product/Service
Tech/Ops
Project Specific
Project Specific
Executives
Operations
Technology
External Orgs
Functional Experts
Operational Experts
Technology Experts
External Experts
Section 2
Decentralized

## Slide 34: Agile Team Roles & Responsibilities
OWNER
Ensures the Right Capability is Built
Defines capabilities to be built
Prioritizes iterations.
Updates Sr. Stakeholders
Consolidates input from Architect & Project Lead
ARCHITECT
Ensures the Capability is Built Right
Brings technical expertise
Oversees solution testing
Validates design
Provides input to Owner for approvals
PROJECT LEAD
Coordinates the Capability Build
Coordinates activities
Integrates functional teams
Plans & controls the iteration
Provides status to Owner.
Facilitates team meetings.
TEAM MEMBERS
Builds the Capability
Provides Lead with activities, durations, and dependencies
Performs the work
Provides updates to Lead
Coordinates change of scope
Performs testing and deployment of solution.
Section 2

## Slide 35: First a Minimum Viable Product (MVP)
Start with Basics & Grow
Minium Viable Product
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE ITERATIONS
Market Growth / Sustainable Products & Services
Section 2
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE
VALUE

## Slide 36: Predictive into Adaptive
Section 2
MVP
Iteration A
Iteration B
Iteration C
Iteration D
Iteration E
Iteration F
ITERATIONS
YEAR - 1
YEAR - 2
Mth1
Mth2
Mth3
Mth4
Mth5
Mth6
Mth7
Mth8
Mth9
Mth10
Mth11
Mth12
Mth1
Mth2
Mth3
Mth4
Mth5
Mth6
Mth7
Mth8
Mth9
Mth10
Mth11
Mth12
Planning
Building/Testing
Review/Feedback
Approve
Adjust/Track
Predictive
Adaptive
Hybrid

## Slide 37: Generating a Pipeline (Backlog) of Value Iterations/Sprints
Call Them Whatever You Like
Internal Controls
External Controls
Community Access
Cost of Service
Mission Alignment
Staff Engagement
Use of Service
Community Feedback
Communications
Technology
Funding
Paid Staffing
Investment in Growth
Transparency
Facilities/Locations
Tracking/Report Outcomes
Impact Analysis
Service Planning & Design
Leadership Support
Learning & Adjusting
Partner Relationships
Equipment
Volunteers
Sustainable Solution
Backup Support
Service Needs
Government Policies
Local 501 c3 Organizations
Volunteer Engagement
Funding Sources
Community Perception
Charity Rating Platforms
Partner Access/Support
Political Affiliations
What is the Market/Community/Customer Saying?
Section 2

## Slide 38: Strengths-Weaknesses-Threats-Opportunities
Strengths
Forces that are unique to the organization
Core competencies: Skills, operating capabilities & differentiators
Resources: People & Capital
Weaknesses
Forces that limit an organizations value proposition
Capabilities, skills, capital investments, etc.
Opportunities
Forces that can be capitalized
Factors
Political, Economic, Social-Cultural, Technological, Environmental, Legal, etc…
Threats
Forces that can cause disruptions
Factors
Political, Economic, Social-Cultural, Technological, Environmental, Legal, etc…
External Forces
Internal Forces
Opportunities-Strengths (OS)
Strategic Thyme(s)
Using strengths to exploit opportunities
Strategy
(O1, S2, S3)
Threats-Strengths (TS)
Strategic Thyme(s)
Using strengths to combat threats
Strategy
(T3, S1, S3)
Opportunities-Weaknesses (OW)
Strategic Thyme(s)
Correcting weaknesses to exploit opportunities
Strategy
(O2, W1)
Threats-Weaknesses (TW)
Strategic Thyme(s)
Correcting weaknesses to combat threats
Strategy
(T4, W3)
Value Propositions from a SWOT
Section 2

## Slide 39: Start the Pipeline at Project Initiation
The Big Idea
100 Pieces of Value to Create
Minimum Viable Product
60 Pieces for Base Solution
Value Iteration
1 Piece of Added Value
Value Iteration
1 Piece of Added Value
Value Iteration
1 Piece of Added Value
Value Iteration
1 Piece of Added Value
Value Iteration
1 Piece of Added Value
Section 2

## Slide 40: Managing a Pipeline of Value Driven Ideas
Develop Initial list of Value Propositions
Prioritize the Top 3-5 Initiatives
Implementation of first Value Iteration
Review How the Implementation Went
Reprioritize the Pipeline and Rethink Approach
Get in A Rhythm
Section 2

## Slide 41: Value Iteration/Sprint Management
Prioritized Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Resources Needed
Resources
Resources
Resources
Expected Outcome
Outcome
Outcome
Outcome
#
1
2
3
Service/Area
Service/Area
Service/Area
Service/Area
Pipeline/Backlog of Iterations/Sprints
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Section 2

## Slide 42: Project Initiation
Getting Things Going
Getting the Band Together
Section 3

## Slide 43: A Journey in Project Management
Start it
Plan it
Do It
Close It
Adjust It
I need you to lead a project.
No problem.
Let’s Take it Together
Section 3

## Slide 44: Project Assignment
Project Managers Are Normally Assigned
Okay, now what?
What’s the scope?
What are the expectations?
  money, time, deliverables
What skills are needed?
Who to engage first?
What’s the exposure?
Who are the key stakeholders?
What are the constraints?
What are the assumptions?
Section 3

## Slide 45: Getting it Going
Project Initiation: Putting the Band Together and Creating the Playlist
Why this project, what are the expected outcomes?
What’s the initial understanding of scope, what’s in, and what’s out?
Who are the resources needed and where do they sit?
What are the schedule expectations?
Schedule
How are communications managed
What are the potential risks?
What are the current assumptions and constraints?
Who are the initial stakeholders?
Section 3

## Slide 46: What Style of Project
Depends on What We Know or Think We Know
Section 3
Predictive
Longer View of Expected Results or Needs
Adaptive
Short View of Results or Needs, Uncertainty of Future
Hybrid
Understand Midrange Needs, Future Needs Unpredictable

## Slide 47: Project Environmental Factors
Internal Environmental Factors
Process Assets
Governance Documentation
Data Assets
Knowledge Assets
Security & Safety
Culture, Structure, & Governance
Geographic Distribution
Infrastructure
Technology & Software
Resource Availability
Employee Capabilities
External Environmental Factors
Marketplace Conditions
Social & Cultural Conditions
Regulatory Environment
Commercial Databases
Academic Research
Industry Standards
Financial Considerations
Physical Environment
Section 3

## Slide 48: Project Performance Domains
Stakeholders
Team
Development Approach & Life Cycle
Planning
Project Work
Delivery
Measurement
Uncertainty
Section 3
Integrated
Interdependent
Concurrent

## Slide 49: Narrowing the Knowledge Gap
When do Project Managers Engage?
Section 3
Ideation / Commercial Notification
Knowledge Gap
Project Team Engagement
1st Level Cost Estimates, Schedule, Scope, Resourcing, Risk
Project Approved & kick-off Sessions
Time
Ideation & Approvals
Initiation & Planning
Requirements / Discovery / Revised Cost / Updated Timelines
Acceptance of Baseline Schedule, Cost, Scope, Risk, Etc.
Design/ Develop / Test / Train
Scope, Schedule, Cost Controls
Solution Design / Core Development / Unit Testing
User Acceptance Testing, End User Training
Integration & End-to-End Testing / Training Data Setup
Go-Live Support / Hypercare
Steady State
Transition to
Run the Business
Support
Close
Prj. Approvals
Getting it Going
Lifecycle
Earlier the Better

## Slide 50: Project Charter
Formal Initiation Document
Charter
Scope
People
Time
Money
Communicate
Risks
Constraints
Project Charter
Executive Summary
Formalizes the Project
Used at Initiation
Not a Living Document
Guides the Project Start
Communications Tool
Can be Contract Appendix
Sets Initial Scope Baseline
Not all Charters are Equal
Section 3

## Slide 51: Constraints and Assumptions
Constraints
Must be completed by.
An agreement ends on this date.
System is being sunset on this date.
We only have this amount approved to spend.
There’s a holiday weekend where we should go live.
We need to have all agreed to functionality on day one.
A key resource is out of pocket during a specific period.
Assumptions
When we want to go live there will be a low impact on stakeholders.
The project will deliver an expected value within a short time.
If we deliver this project the demand will be there.
The cost we estimated in the approvals will be all that’s needed.
We have the skill and abilities to implement this.
Section 3

## Slide 52: Team Exercise: Kick Starting the Project
What’s the project all about?
Project Initiation
What’s the project about?
Who needs to be involved?
When is it expected to be ready?
Constraints and assumptions?
How will the project team communicate?
How is the project funded?
Any big risks?
Team Exercise

## Slide 53: Project Planning
Who, What, When, How
Baselining Expectations
Section 4

## Slide 54: Planning for What?
What Tools/Processes/Methodologies Planned to Use
Project Plan
Work Breakdown Structures
Activity Dependencies and Durations
Baselined Scope of Work Demonstrated
Subject Mater Experts Input and Buy-in
Activities with Ownership
Resource Plan
Sponsors, Stakeholders, Decision Makers
Internal & External
Functional Leads & Work Product Owners
Available Contact Information
Connected to Project Plan
Communications
Executive Sponsor Status Reporting
External Communications
Project Team Communications
Frequency/Methods/Content/Audience
Cost Control
Baselined Budgets
Estimated Dates of Spend
Approval Processes for Changes
Cost Reporting
Scope Control
Baselined Scope Document
Scope Change Process & Approvals
Connected to Project Plan & Cost Control
Risk Control
Future Looking Threats and Opportunities
Probabilities and Impact Responses
Connected to Project Plan
Issues Lists are Separate and Immediate
*Others Not Shown and Not Every Project Requires Everything
Section 4

## Slide 55: The Hardest Thing to See
7
7.5
7.1
7.2
7.3
7.4
1
1.1
1.2
1.3
1.4
2
2.1
2.2
2.3
9
9.2
9.5
9.4
9.3
9.1
6
6.1
6.2
6.4
6.3
10
10.1
10.2
4
4.2
4.3
4.1
5
5.2
5.4
5.5
5.1
5.3
5.6
3
3.1
8
8.1
8.4
8.3
8.2
Think About the Dots As
Scope
Schedules
Cost
Resources
Risks
Communications
What’s Missing?
Section 4

## Slide 56: Project Management is a Team Sport
Treat it That Way
Section 4

## Slide 57: Narrowing the Knowledge Gap
Building Structure with Flexibility
Section 4
Ideation / Commercial Notification
Knowledge Gap
Project Team Engagement
1st Level Cost Estimates, Schedule, Scope, Resourcing, Risk
Project Approved & kick-off Sessions
Time
Ideation & Approvals
Initiation & Planning
Requirements / Discovery / Revised Cost / Updated Timelines
Acceptance of Baseline Schedule, Cost, Scope, Risk, Etc.
Design/ Develop / Test / Train
Scope, Schedule, Cost Controls
Solution Design / Core Development / Unit Testing
User Acceptance Testing, End User Training
Integration & End-to-End Testing / Training Data Setup
Go-Live Support / Hypercare
Steady State
Transition to
Run the Business
Support
Close
Prj. Approvals
Getting it Going
Lifecycle

## Slide 58: Estimating
Levels of Accuracy
Range
75%
0%
25%
50%
-25%
Time
Accuracy
Section 4

## Slide 59: Resource Planning
Section 4
Project Manager
Functional Area
Functional Area
Functional Area
Skills
Skills
Skills
Skills
Skills
Skills
Stakeholders
Leadership
Sponsors
Identify Needed Skills & the People With Them
External Organizations
Technology
Specialized Equipment
Facilities / Buildings
Identify Other Needed Resources

## Slide 60: Schedule Planning
Section 4
Tool(s) to use
Defining the work
Linking work with dependencies
Applying durations to the work
Allocating resources
A critical path that makes logical sense
Getting a schedule to baseline

## Slide 61: Communications Planning
Section 4
HOW
E-mail
Video Calls
Face-to-Face
Push Status Reports
Pull Status Reports
Stand-Up Meetings
WHO
Internal/External
Stakeholders
Project Team
Executive Leadership
Functional Leaders
Organizational Wide
WHAT
Project Status
Challenges / Risks
Scope Changes
Cost Performance
Timeline Updates
Roadblocks

## Slide 62: Cost Planning
Section 4
Cost of Time
Resource Cost
Internal & External
Invoiced or Not
Where are Cost Associated
How to Estimate
How to Track
Travel Expenses
How Travel is Authorized
Where are Cost Associated
Are Cost Marked-Up
How to Estimate
How to Track
Asset Costs
Capital or One-Time
Margin Applied
Where are Cost Associated
How to Estimate
How to Track

## Slide 63: Scope Planning
Section 4
Who authorized current scope of work?
How will scope be validated?
Once agreed, how will scope be controlled?
Who approves changes to scope?
How to build the scope of work into a timeline?

## Slide 64: Risk Planning
Section 4
How will project disrupters be identified?
Who makes decisions on what to accept?
How will risks be evaluated?
Will this be done at all?

## Slide 65: Team Exercise: Building the Foundation
Project Planning
What needs to planed?
How accurate will you be?
Who approves the plans?
Team Exercise

## Slide 66: Resource Management
People, Equipment, Technology, etc.
Borrowed or Owned
Section 5

## Slide 67: Functions Associated with Projects
People Drive Project Delivery
Section 5
Customer: Individual or group who requested or is funding the project.
End User: Individual or group who experiences the direct use of the project deliverable.
Provides Oversight & Coordination
Presents Objectives & Feedback
Facilitates & Support
Provides Business Direction & Insights
Maintains Governance
Provides Resources & Direction
Performs Work & Contributes Insight
Applies Expertise

## Slide 68: Coordinating the Work
Decentralized
Team Members Self-Organize & Self Manage
Centralized
Leadership and Guidance of a Project Manager
Section 5
Project Manager
Functional Leaders
Functional Team Members
Servant Leader
Facilitator
Self
Organizing
Functional Team Members

## Slide 69: Stakeholders
Stakeholder
Individual, group, or organization that touches the project or outcome of the project.
Identify
Prioritize
Monitor
Engage
Understand
Analyze
Engagement
Section 5
Stakeholder Aspects
Power, Impact, Attitude, Beliefs, Expectations, Degree of Influence, Proximity to the Project, Interest in the Project, and Other Interactions

## Slide 70: Project Team Allocation
Who Owns the Team Resources
Projectized
Project
Manager
Direct Reporting
Matrix
Project
Manager
Team
Technology
Team
Human Resources
Team
Finance
Team
Engineering
Team
Marketing
Borrowed Resources
Section 5

## Slide 71: Standard Team Structure Example
Different Projects = Different Resources
Core Business
Project Manager(s)
PROJECT
External Org.
Sponsor(s)
Project Manager
Integration Lead(s)
Application Lead(s)
Hardware Lead(s)
Tech Security Lead
Legal Lead
Finance Lead
Compliance Lead
Technology Project Manager
Operations Lead
Human Resource Lead
Marketing Lead
Section 5

## Slide 72: Cross Organizations-Countries-Continents
Distributed Project Teams
Time Zones
Cultures
Policies
Leadership Direction
Government
Skills & Capabilities
Availability
Desire
Challenges to Resource Management
Transparency
Respecting Differences
Setting Team Norms
Coordination of Events
Working Together
Section 5

## Slide 73: Adaptive (Agile) Team Structure
Different Value Iterations = Different Resources
ARCHITECT
Ensures the Capability is Built Right
PROJECT LEAD
Coordinates the Capability Build
TEAM MEMBERS
Builds the Capability
OWNER
Ensures the Right Capability is Built
STAKEHOLDERS
SPECIALISTS
Product/Service
Tech/Ops
Project Specific
Project Specific
Executives
Operations
Technology
External Orgs
Functional Experts
Operational Experts
Technology Experts
External Experts
Section 5

## Slide 74: Factors that Limit Strategic Results
Vision
Actionable
Strategy
Capabilities
Incentives
Resources
Urgency
Success
Confusion
False Starts
Anxiety
Restraint & Resistance
Frustration
Apathy
Lacking Vision
Lacking Actionable Strategy
Lacking Capabilities
Lacking Incentives
Lacking Resources
Lacking Urgency
Success Factors
Transparency
Stakeholder Engagement
Communications
Involvement
Limiting Factors
Disengagement
Organizational Alignment
Resource Capabilities
Contradicting Priorities
Section 5

## Slide 75: Culture
What Makes an Organizational or Team Culture
Behaviors
Beliefs
Culture
Section 5

## Slide 76: Culture Should be Visible
Alignment with Stated Values or Beliefs
Sample Stated Values or Beliefs
Integrity
Innovation
Accountability
Respect
Teamwork
Trust
Creativity
Adaptability
Leadership
Transparency
Diversity
Section 5
Innovation
Learn from Failure
Experiment
Continuous Learning
Continuous Improvement
Formal Training
Shared Experiences
Low Risk Opportunities
Challenging Opportunities
Formal CI Programs
Reports to Sr. Leadership

## Slide 77: What Comes First, Beliefs or Behaviors?
Changing Culture Requires Changing Both
Behaviors
Actions we take
Decisions we make
Tasks we perform
How we work
How we interact
Developed over Time
Beliefs
How we think
Input into Decisions
Drives commitments
How we trust
Where we get information
Developed over time
This isn’t a chicken or egg problem
Section 5
Technology Advances
Working Locations
Global Travel
Climate Change
Scientific Advances
Medical Advances
Leadership Advances
Forced Behavioral Changes
Enhances jobs, not eliminates
Remote work is beneficial
People want the same things in life
Fossil fuels to sustainable solutions
The Earth is a sphere
Cancer doesn’t always kill
People need more than a paycheck
Beliefs that Followed

## Slide 78: Change a Culture to Deliver Value
Understand Why the Change is Needed
Cyber security is a threat to data integrity and ransom demands.
How Wide the Change is
All users with access to company email, all applications, and have unique user login credentials.
What Behaviors Need to Change
Password credentials change every 90-days, and double security access required for certain applications.
Plan to Socialize the Change
Development of communications material and lists of people impacted by the change.
Socialize the Change
Open and circular communications, answer all questions, and actively listen to concerns.
Build a Team of Champions
Pilot the changes with people that have the greatest connections to those impacted, get feedback and adjust.
Implement in Phases
Make the changes as quickly as possible, but in manageable group sizes, and apply extra support.
The Behavioral Challenge
People like single login access to a system and believe additional steps are unnecessary.
Culture to Change
Belief in the Change Comes Much Later
Section 5

## Slide 79: Capital or One-Time Resources
Facilities
Infrastructure
Office Equip.
Specialty Equip.
Capital Resources
Depreciable Assets
Technology
Operating Systems
Travel
Construction Equip.
Outsourced Experts
Short Term Rentals
One-Time Project Resources
Short-Term Needs
Specialty Tools
Short-Term Storage
Section 5

## Slide 80: Team Exercise: Resourcing the Project
Resource Planning
Who are the people?
What other resources are needed?
Where are the challenges?
Team Exercise

## Slide 81: Communications Management
How, When, Who, and What
Audience Drives Style
Section 6

## Slide 82: Forms of Communications
Section 6
Content
Written or Visual
E-mails, Memos, Text Messaging, or any form of Written Report
Charts, Graphs, Status Lights, or any Visual Indicator
Physical
Verbal or Audible
Face-to-Face, Phone, Video Conferencing, or any form of Direct Connections
Video Content, Recorded Messaging, or any form of Recorded Communications
Delivery
Push or Pull
PUSH
E-mail Reports, Status Meetings, Auto Generated Reports, and other forms of Distributed Communications
PULL
Report Repositories, Portfolio Tools, and other forms of Communications Storage and Retrieval
Formal
Presentations, Project Reviews, Briefings . . .
Informal
General Conversations, Brief Notes, Text . . .

## Slide 83: Communications Loop
Message Encoding
Sender
Message Decoding
Receiver
Noise
Message
Electronic Communications
Audio Communications
Direct Communications
Feedback
Response
Section 6

## Slide 84: Project Engagement of New People
Getting Them Up-To Speed
Project Team
Project Charter
Team Meetings
Status Reports
Document Access
Detailed Reviews
Leadership
Project Briefings
Status Reports
Project Charter
Executive Summary
Sponsors
Project Briefings
Status Reports
Project Charter
Sponsor Summary
Stakeholders
Project Briefings
Status Reports
Narrow Focused Report
Section 6

## Slide 85: Communications Channels
Why Planning and Controlling Communications is Important
Project Team Members = N
N(N-1)/2 = Communications Channels
N=10 People
10(10-1)/2 = 45 Channels
Watch Outs
Quiet Team Members
Overbearing Team Members
Focus on Issues, not People
Focus on Present & Future, not Past
Section 6

## Slide 86: Status Reporting
What-When-Who-How
Executives / Sponsors
External Partners
Internal Functional Leaders
Project Team Members
Key Milestones, Risks, Cost, & Exec. Decisions Needed
Integrated Activity Status, Issues, Action Items, & Risk Review
Milestones Review, Resource, Risks, Issues, and Needs
Activity Status, Milestones Review, Issues, Risks, & Constraints
Type of Report Content
Type of Status Reports
Frequency
(Weeks)
4-5
1-3
1-3
1-2
Note: Project complexity, organizational importance, levels of risk, and other factors will change audiences, content, and frequencies.
Section 6

## Slide 87: Example Status Report
Executives / Sponsors / External / Internal (Modified for Needs)
Report Date: 15 JAN 25
Project: Project #15976
Project Manager
Stephanie Rodrigues
Tech Project Manager
Kendrick Emanual
Tracking
Challenges
Critical
Status Indicators
Holding
Improved
Decreased
Tracking Direction
Project Status
Comp:
25%
Resources:
Schedule:
Scope:
Risks:
Cost:
Key Milestones / Key Schedule Dates
Milestone
Planned Date
Status
Contracting for Services Completed
08 OCT 24
100%
Scope of Services/Business Requirements Completed
10 DEC 24
75%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
Challenge / Issue / Actions
Resolve Date
Status
Scope Approval Delaying Development
20 JAN 25
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
Support Needed / Decision to be Made
From / Owner
Status
Scope Approval Authorities – Who?
Exec Sponsors
Pending
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
Section 6
What’s the greatest value in creating this report?

## Slide 88: Scope Management
Understanding it & Controlling it
Not all Change is Bad
Section 7

## Slide 89: Scope: The Delivery of Value
Requirement: “A condition or capability that is necessary to be present in a product, service, or result to satisfy the business need.”
PMBOK® 7th Edition
Section 7
Project Scope
Functionality
User Experience
Look & Feel
How things work
How they respond
Information provided
How users interact
Value provided
Ease of use
Overall appearance
Quality of materials
Navigation
Requirements
Requirements
Requirements
Scope Decomposition

## Slide 90: Requirement Attributes
Functional vs. Nonfunctional
Clear
Concise
Verifiable
Consistent
Complete
Traceable
Only one interpretation
Use as few words possible
A way to verify completion
No contradicting requirements
Combined requirements represent all project needs
They can be identified and followed through the projects
Section 7
Functional
Action Words Describing Functionality Required to Meet Needs
Nonfunctional
Quality Words Describing the Look & Feel, the Appearance

## Slide 91: Capturing Requirements
Section 7
Participants
Functional Stakeholders
Operational Stakeholders
Leadership
End Users
Methods
Use Cases
Observations
Interviews
Prototyping
Requests for . . .
Information
Quotes
Proposals

## Slide 92: The Life Cycle of a Requirement
Requirement Traceability
Requirement
Defined
Added to Scope & WBS
Design
Develop
Test
Train
Execute
Support
Section 7

## Slide 93: Scope Decomposition
Breaking Requirements Down – Work Breakdown Structure
Section 7
1.0 Requirement
Project Scope (Delivery Expectation)
2.0 Requirement
3.0 Requirement
1.1 Task / Work Package
2.1 Task / Work Package
3.1 Task / Work Package
1.2 Task / Work Package
2.2 Task / Work Package
3.2 Task / Work Package
1.3 Task / Work Package
2.3 Task / Work Package
1.3.1 Sub Work Package
1.3.2 Sub Work Package
1.3.3 Sub Work Package
1.4 Task / Work Package
3.2.1 Sub Work Package
3.2.2 Sub Work Package
3.3 Task / Work Package
2.1.1 Sub Work Package
2.1.2 Sub Work Package
2.1.3 Sub Work Package
Project Scope
The work performed to deliver a product, service, or result with the specified features and functions
Product Scope

## Slide 94: Work Breakdown Structures (WBS)
WBS is Not
Schedule
Responsibility Matrix
Time Oriented
No Durations
No Dependencies
WBS Benefits
Prevents work slipping through the cracks
Helps the team understand where they fit
Helps prevent changes
Basis for estimating cost, resources and time
Helps with team buy-in
Section 7
2.1.0 Systems Testing
2.1.1 Unit Testing
2.1.2 Integration Testing
2.1.3 User Testing
2.1.1.1 Write Test Scripts
2.1.1.2 Create Test Data
2.1.1.3 Perform Tests
2.1.1.4 Validate Results
2.1.1.5 Adjust & Correct
2.1.1.6 Retest & Adjust
2.1.1.7 Accept Testing
Use Verbs, Action Words, and be Clear in Description
Work Packages Should be in Manageable Chunks, Not To-Do List Size

## Slide 95: Approving Scope
Scope Planning
Requirements are Defined
Requirements Documented
In Scope & Out of Scope is Clear
Scope Control is Planned
Scope Approvals
Approval Authority Defined
Scope Reviews
Feedback Provided
Adjustments Made
Tentative Approvals Provided
Formal Approvals Given

## Slide 96: Controlling Change
Section 7
Is the change required for the MVP?
“During the life of a project change is inevitable.”
Define the Change
Document the Change
Approve the Change
Understand Project Impact
Schedule the Change
Cost
Schedule
Resources
Risks
Change Request
Scope Document
Status Reports
Written / Verbal
Documented
Communicated
Why the Change
Who Requested
Value Delivered
Build WBS
Add to Schedule

## Slide 97: Team Exercise: Scope Management
Scope Planning
Work Breakdown Structure (WBS)
How is scope approved?
How are changes to scope managed?
Team Exercise

## Slide 98: Schedule / Time Management
Linking the Parts that Deliver Value
Listen to the Experts
Section 8

## Slide 99: Common Terms in Schedule Management
Constraints
Assumptions
Decomposition
Activities
Milestones
Critical Path
Dependencies
Baseline
Slack & Lag
Work Package
Section 8
Crash & Fastrack

## Slide 100: Decomposing the Work Down into Digestible Groups
Work Breakdown Structures
Complexity determines planning tool
  Number of activities, resources, scope, etc.
Activity can represent a few days to a few weeks of effort
  Can be hours or workdays
Logical buckets are good, but not absolute
  Importance is listing the activity somewhere
Project
Summary Level 1.0
Summary Level 2.0
Summary Level 3.0
Activity 1.1
Activity 1.2
Activity 1.3
Activity 2.1
Activity 2.2
Activity 2.3
Summary Level 3.1
Activity 3.11
Activity 3.12
Activity 3.2
Activity 3.3
Section 8
Planning Tools

## Slide 101: Estimating Time
Program Evaluation Review Technique
= Estimate
Expert Judgement
Analogous Estimating
Quantitatively Based Durations
Bottom Up
Top Down
PERT Estimates
Section 8

## Slide 102: Applying Time to Activities
Apply best estimate of time to complete activities
Order & sequence does not matter
  That comes next
Project
Summary Level 1.0
Summary Level 2.0
Summary Level 3.0
Activity 1.1
Activity 1.2
Activity 1.3
Activity 2.1
Activity 2.2
Activity 2.3
Summary Level 3.1
Activity 3.11
Activity 3.12
Activity 3.2
Activity 3.3
Durations
WK 1
WK 2
WK 3
WK 1
WK 2
WK 1
WK 2
WK 1
WK 1
WK 2
WK 3
WK 1
WK 2
WK 1
WK 2
WK 1
WK 1
WK 2
WK 3
WK 1
3
3
3
2
2
3
1
3
2
3
2
2
1
3
1
WKS
WK 1
WK 2
WK 3
WK 4
WK 5
WK 6
WK 7
Summary Level Time
Summary Level Time
Summary Level Time
Summary Level
Section 8

## Slide 103: Dependencies
Create Logic and Order Trough Linkage
Mandatory
Discretionary
External
Internal
Nature of the work drives the dependency
Project preferences drive the dependency
Outside, uncontrolled activities drive the dependency
Organizationally controlled activities drive the dependency
Section 8
Finish to Start
Activity
Activity
F
S
Finish to Finish
Activity
Activity
F
F
Start to Start
Activity
Activity
S
S
Start to Finish
Activity
Activity
S
F
When One Finishes the Other Can Start
They Both Need to Finish Together
They Both Need to Start Together
When One is Starting the Other Must be Finishing

## Slide 104: Critical Path & Milestones
“A milestone marks the beginning or end of something”
Milestones Have Zero Duration
Section 8
A
6 Days
D
4 Days
F
7 Days
E
8 Days
G
5 Days
B
5 Days
H
7 Days
C
8 Days
33 Days
“A critical path is the shortest time from start to finish”
Start
Finish

## Slide 105: Linking the Activities Builds the Schedule
FS
Finish-Start
SS
Start-Start
FF
Finish-Finish
SF
Start-Finish
Dependencies
Project
Summary Level 1.0
Summary Level 2.0
Summary Level 3.0
Activity 1.1
Activity 1.2
Activity 1.3
Activity 2.1
Activity 2.2
Activity 2.3
Summary Level 3.1
Activity 3.11
Activity 3.12
Activity 3.2
Activity 3.3
WK 1
WK 2
WK 3
WK 1
WK 2
WK 1
WK 2
WK 1
WK 1
WK 2
WK 3
WK 1
WK 2
WK 1
WK 2
WK 1
WK 1
WK 2
WK 3
WK 1
7
6
3
2
2
4
1
3
2
5
3
2
1
3
1
WKS
Summary Level Time
Summary Level Time
Summary Level Time
WK 1
WK 2
WK 3
WK 4
WK 5
WK 6
WK 7
Project Level Time
Summary Level Time
FS -1wk
SS +1wk
SS
FS
FS
FS
FS -1wk
FS
FF
Critical Path
Float/Slack
Section 8

## Slide 106: Crashing & Fast Tracking
Section 8
Crashing a Timeline
Standard Task Duration
Added Resource Duration
Fast Tracking a Timeline
Standard Dependency
Fast Tracked Dependency
F
S
F
S – 10days
Adding resources to complete the work in a shorter period
Starting work before completely ready to start

## Slide 107: Schedule Performance
Earned Value or Best Guess
Rough Guess Estimates
00% = Not Started
25% = Activity Started
50% = Half-Way Through
75% = Getting Close to Finish
100% = Finished, No Additional Work
NOT COMPLICATED
Section 8
Schedule Performance Index (SPI)
SPI < 1.0 = Behind Schedule
Actual Work is 50% Completed
Planned to be 75% Completed
BCWP = $500
Budgeted Cost of Work Performed
Estimated Cost
100 Hrs @ $10 per Hr
BAC = $1,000
Budget at Completion
COMPLICATED
BCWS = $750
Budgeted Cost of Work Scheduled
SPI = 67%
Schedule Performance

## Slide 108: Update Activities with Owners Input
Project
Summary Level 1.0
Summary Level 2.0
Summary Level 3.0
Activity 1.1
Activity 1.2
Activity 1.3
Activity 2.1
Activity 2.2
Activity 2.3
Summary Level 3.1
Activity 3.11
Activity 3.12
Activity 3.2
Activity 3.3
WK 1
WK 2
WK 3
WK 1
WK 2
WK 1
WK 2
WK 1
WK 1
WK 2
WK 3
WK 1
WK 2
WK 1
WK 2
WK 1
WK 1
WK 2
WK 3
WK 1
7
6
3
2
2
4
1
3
2
5
3
2
1
3
1
WKS
Summary Level Time
Summary Level Time
Summary Level Time
WK 1
WK 2
WK 3
WK 4
WK 5
WK 6
WK 7
Project Level Time
Summary Level Time
100%
25%
Started
50%
About ½ Way
75%
Almost Done
100%
Finished
% Complete
0%
Not Started
75%
100%
25%
75%
25%
Critical Path
Float/Slack
Section 8
Current Date

## Slide 109: Narrowing the Knowledge Gap
Moving From Planning to Doing the Work
Section 8
Ideation / Commercial Notification
Knowledge Gap
Project Team Engagement
1st Level Cost Estimates, Schedule, Scope, Resourcing, Risk
Project Approved & kick-off Sessions
Time
Ideation & Approvals
Initiation & Planning
Requirements / Discovery / Revised Cost / Updated Timelines
Acceptance of Baseline Schedule, Cost, Scope, Risk, Etc.
Design/ Develop / Test / Train
Scope, Schedule, Cost Controls
Solution Design / Core Development / Unit Testing
User Acceptance Testing, End User Training
Integration & End-to-End Testing / Training Data Setup
Go-Live Support / Hypercare
Steady State
Transition to
Run the Business
Support
Close
Prj. Approvals
Getting it Going
Lifecycle
Doing the Work
Transferring
Project Intensity

## Slide 110: Doing the Work, Controlling the Project
Activity Updates
Updates to durations & dependencies
Updates to activities % complete
Update activity owners
A critical path that makes logical sense
Status Reporting
Audience appropriate reporting
  Executive sponsor reporting
  External organization reporting
  Stakeholder reporting
  Team reporting
Scope Control
Understand impact of change
  Cost, schedule, resources, etc.
Approvals of change
Build change into the plan/schedule
Issues Mgt
Tracking and updating issues
  These are issues happening, not risks
Understanding impact to project
  Cost, schedule, quality, etc.
Risk Control
Monitor and adjust identified risks
  Only those with planned responses
Update project plan as needed
Low risks without planned responses let ride but still monitor
Resource Mgt
Changing functional resources need updated
Adjust deliverables where needed
  Get buy-in from new resources
*Others Not Shown and Not Every Project Requires Everything
Section 8

## Slide 111: Team Exercise: Time Management
Schedule Planning
Applying Time to WBS
Linking Activities
What’s the critical path?
When is the project is ready to go?
Team Exercise

## Slide 112: Cost Management
Initial versus Reality
Estimating and Adjusting
Section 9

## Slide 113: Estimating Cost
No Different Than Estimating Time
Program Evaluation Review Technique
= Estimate
Expert Judgement
Analogous Estimating
Quantitatively Based Estimates
Bottom Up
Top Down
PERT Estimates
Section 9

## Slide 114: Configuring for Cost of Resources
Quantitatively Based but with Best Guess Assumptions
# | Resource | Role | Existing $ (per Hour) | Incremental $ (per Hour)
1 | Senior Project Manager | Project Management | $125 | 
2 | Business Analyst | Business Requirements | $70 | 
3 | Training Manager | Testing & Training | $0 | $100
4 | Engineer | Operations Design | $125 | 
5 | Operations | Operations Design | $95 | 
6 | IT Project Manager | Project Management | $115 | 
7 | IT Development Lead | Technology Design | $95 | 
8 | Integration Lead | Systems Integration | $95 | 
9 | Applications Lead | Applications Development | $95 | 
10 | Infrastructure Lead | Equipment & Network | $0 | $125
Cost of Resource Configuration
Travel Cost Est. Configuration
Category | Cost
Airfare (per Trip) | $700
Lodging (per Day) | $250
Rental Car (per Day) | $80
Meals (per Day) | $100
Misc. Travel (per Day) | $10
Project Duration Est.
(By Project Phase)
Project Phase | Wks | Est. Start | Est. Finish
Project Initiation | 4 | Mar 03, 2025 | Mar 31, 2025
Discovery & Design | 10 | Mar 31, 2025 | Jun 09, 2025
Development & Testing | 12 | Jun 09, 2025 | Sep 01, 2025
Training, Go-Live, & Close | 10 | Sep 01, 2025 | Nov 10, 2025
Total Est. Project Duration | 36 | Mar 03, 2025 | Nov 10, 2025
Section 9

## Slide 115: Applying Next Level Assumptions to Resource Estimates
Section 8
Tools help in estimates, but they’re still best educated guesses.

## Slide 116: Cost Performance
Not Easy
Challenges to Cost Management
Access to Data
Accuracy in Data
Timeliness of Data
Cross Functional Data Integration
Project Mgt. Resource Support
Section 9
Cost Performance Index (SPI)
CPI < 1.0 = Behind Schedule
Budgeted to Spend
$50,000
Actual Spend
$60,000
BC = $50,000
Budgeted Cost
Cost Variance = $10,000
COMPLICATED
AC = $60,000
Actual Cost
CPI = 83%
Cost Performance
Evaluates by work package overall cost value
If the CPI < 1.0 The activity is running over budget
Cost Performance: For Every $ Spent, There’s $0.83 of Budgeted Value

## Slide 117: Tracking Resource Actual Cost
Many Methods for Capturing Resource Cost, None are Easy
Section 9

## Slide 118: Estimating Non-Resource Cost
Section 9

## Slide 119: Team Exercise: Cost Management
Cost Planning
What are the cost elements?
What’s the estimated budget?
What’s the level of confidence?
How will cost be tracked?
Team Exercise

## Slide 120: Risk Management
Threats & Opportunities
Probabilities & Impact
Section 10

## Slide 121: What is Risk
Section 10
Things that may derail the project
Negative impact to time, cost, scope, etc.
Response plans for actions
Things that may improve the project
Positive impact to time, cost, scope, etc.
Response plans for actions
“A risk is an uncertain event or condition that, if it occurs, can have a positive or negative effect on one or more objectives”
PMI® PMBOK® 7th Edition

## Slide 122: Risks or Issues
Risks
They May Happen
Possibility of a Disruption
Possibility of an Opportunity
Mitigation Responses
Input into Project Activities
Response to Probability or Impact
Issues
It’s Happening
Present Challenge
Immediate Response
Managed at Occurrence
Reduce Immediate Impact
Section 10

## Slide 123: Identifying Risks
Find in the WBS
Use Experience
Brainstorm Considerations
Look Externally, Internally, Operationally, Technically, Functionally, etc…
Section 10

## Slide 124: Three Choices Affecting Two Things
PROBABILITY
IMPACT
Accept It!
Change It!
Leave It!
Section 10
How likely is it to happen?
If it happens, what does it effect?
If it happens, when is that expected to be?
Can it happen more than once?

## Slide 125: Risk Responses
Accept It, Change It, or Leave It
No response planning
Manage if it happens
Monitor until action needed
Remove scope from project
Plan actions to remove
Get approvals for removal
Actions to change probability
Actions to change impact
Plan mitigation actions
Risk ownership transferred
Monitor & control as needed
Formal agreements if needed
Response Should Be
Appropriate for the significance of the risk
Cost effective
Realistic within the project context
Agreed to by relevant stakeholders
Owned by a responsible person
Section 10

## Slide 126: Breaking Down Risk Management
Qualitative or Quantitative
Identification
Description of Results
Understanding Impact
Calculating Probability
Decisions on Response
Monitor & Control
Response Application
Naming the risk
What happens and what does it cause
The level of disruption or advantage
The likelihood that it will occur
How we deal with it
Watching it and adjusting strategy
Putting actions into play
Section 10

## Slide 127: Planning & Controlling Risk
Risk Rating Simple Tool
Section 10
Very Low: Acceptance is a normal response.
Low: Acceptance or small actions are a normal response.
Moderate: Actions to lower probability or impact is a normal response.
High: Actions are needed to lower probability or impact.
“Risks are at a specific event, not at the project level.”

## Slide 128: Issues Are Not Risks
Issues are happening; response plans aren’t prepared.
They’ll show in every project and need to be managed.
Use simple or complicated tools but use something.
Section 10

## Slide 129: Team Exercise: Risk Management
Risk Planning
What are some key risks?
How will they be managed?
What are some risks you’re accepting?
Team Exercise

## Slide 130: Transitioning / Closing
Transitioning to Run-the-Business
Moving into Continuous Improvement
Section 11

## Slide 131: Narrowing the Knowledge Gap
Moving From Doing the Work To Transitioning
Section 11
Ideation / Commercial Notification
Knowledge Gap
Project Team Engagement
1st Level Cost Estimates, Schedule, Scope, Resourcing, Risk
Project Approved & kick-off Sessions
Time
Ideation & Approvals
Initiation & Planning
Requirements / Discovery / Revised Cost / Updated Timelines
Acceptance of Baseline Schedule, Cost, Scope, Risk, Etc.
Design/ Develop / Test / Train
Scope, Schedule, Cost Controls
Solution Design / Core Development / Unit Testing
User Acceptance Testing, End User Training
Integration & End-to-End Testing / Training Data Setup
Go-Live Support / Hypercare
Steady State
Transition to
Run the Business
Support
Close
Prj. Approvals
Getting it Going
Lifecycle
Doing the Work
Transferring

## Slide 132: Transitioning to Run-the-Business
Archives
Schedules
Resources
Costs
Risk Tools
Action Items
Performance KPIs
Learnings
Went Well
Had Struggles
Just Went Wrong
Inputs
Stakeholders
External Partners
Internal Partners
Outputs
Run-the-Business
People
Roadmap
Escalations
Future Call Outs
What, How, and Why we Close Projects
Section 11

## Slide 133: Closing
How it Actually Works
Project Manager
Prepares for Closing
Builds the Structure
Populates Project Info
Gathers Input from Team
Finalize Closing Documents
Presents Closing Material
Formally Closes the Project
Team Members
Provides Support Material
Provides Constructive Input
Participates in Closing Sessions
Question Examples
How did the organizations work together?
How could they do better?
What should be repeated?
Were expectations met?
Section 11

## Slide 134: Transfer of Ownership
Project Manager
Operations Owner
Product/Service Owner
Open Issues
Enhancements
Project Documentation
Adaptive
Project Management
Section 11

## Slide 135: Team Exercise: Wrapping up the Project
Final Presentation
Make an executive-level presentation
What is the project about?
Why should it be approved?
What will be the cost?
When can it be ready to go?
Team Exercise

## Slide 136: Project Management into Strategy Management
Strategy Management Tools
Building Teams & Capabilities
Section 13

## Slide 137: Organizationally Deep Strategy, Culture, Mission, Vision, & Values
Highest-Level Organizational Strategy
Highest-Level Mission, Vision, and Values
Business Units / Regional Area Strategy
Mission, Vision, and Values
Functional Area Strategy
Mission, Vision, and Values
Personal Strategy
Mission, Vision, and Values
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Culture
Highest
Lowest
Alignment
Section 13

## Slide 138: What is Strategy?
…Value for Shareholders…
Kaplan, R. S., & Norton, D. P. (2004). Strategy Maps. Harvard Business School Press.
…Competitive Advantage…
Pearce II, J. A., & de Kluyver, C. A. (2015). Strategic Management. Business Expert Press.
…Superior Performance Relative to Competitors…
Rothaermel, F. T. (2017). Strategic Management. McGraw Hill.
…How a Business is Going to Compete…
Porter, M. (1980). Competitive Strategy. The Free Press.
…Plan for Achieving Goals and Objectives…
Nickols, F. (2008). Strategy, Strategic Management, Strategic Planning, and Strategic Thinking.
…Building Capabilities & Competencies…
Gerald Jeffs, Strategy & Project Management Professional
Section 13

## Slide 139: What it is and What it’s not
It’s Not
What you say you’re going to do
What your plans say you’ll do
It Is
What you are doing
What plans are being implemented
Section 13

## Slide 140: What is Strategy Management?
Management, Planning, Controlling, and Adjusting
Markets Served
Value Proposition to Market
Market Potential
Entry into Market
Organization Alignment
Impacted Stakeholders
Organizational Capability
Organizational Motivation
Prioritizations
Strategic Portfolio Pipeline
Competing Forces
Decision Making Authorities
Measurements
Success Factors
Leading & Lagging Indicators
Quantitative vs. Qualitative
Resources
Capabilities & Competencies
Bandwidth & Incentives
People, Capital, Financial, etc.
Pivoting
Sunk Work & Cost Acceptance
Risk Analysis
Executive Feedback Loop
Business Modeling
Writing the Story
What, Who, and How
Financial Flows
Strategic Mapping
Projects Driving Strategy
Impacts of Strategy
Value Returned from Strategy
Section 13

## Slide 141: Mission, Vision, and Values
What, How, and Guiding Beliefs
MISSION
What an organization does
VISION
How an organization delivers on its mission
VALUES
Beliefs of an organization
Different People have Different Definitions
Leadership
Sets Vision & Strategy
Section 13

## Slide 142: Mission, Vision, Values, and Why
What, How, and Guiding Beliefs
MISSION
Delivering Strategic Project Portfolio Management Expertise
VISION
Make Strategy Management Accessible to People, Teams, and Smaller Organizations
VALUES
Trust and Continuous Development
WHY
In helping people, teams, and organizations Improve, we improve ourselves.
Section 13

## Slide 143: Mission Statements
Examples: There is no one set of rules.
General Guiding Principles
Concise description of a company’s general purpose.
  10 to 25 words, keep it simple
Be aspirational & memorable.
  If those close can’t remember it, it isn’t working
  This is for the organization, not the World
Written with multiple audiences in mind.
  Primarily employees
  Public, stakeholders, and customers
Don’t compare yours to others.
  A respected organization doesn’t mean they have a great mission statement
“To bring the best user experience to customers through innovative hardware, software and services.”
“To provide branded products and services of superior quality and value that improve the lives of the world’s consumers, now and for generations to come.”
“To bring inspiration and innovation to every athlete in the world. If you have a body, you are an athlete.”
“Delivering Strategic Project Portfolio Management Expertise.”
Section 13

## Slide 144: Vision Statements
Examples: There is no one set of rules.
General Guiding Principles
Specific but concise, and not overly detailed.
  5 to 15 words, keep it simple
  One or two key points
  Not a catchy phrase, aim for clarity
Inspirational, memorable, and simple
  Easy to focus on and fulfill
  No technical terms or jargon
This is organizational not a World vision
Don’t compare yours to others.
  A respected organization doesn’t mean they have a great vision statement
“Make Strategy Management Accessible to People, Teams, and Smaller Organizations
“Our vision is to be the most trusted and agile partner for meeting diverse educational needs.”
“To make people happy.”
“Spread ideas.”
“We ignite opportunity by setting the world in motion.”
Section 13

## Slide 145: Values, Beliefs, or Behaviors
Examples: There is no one set of rules.
General Guiding Principles
Serve as a guide for behavior
Can shape the culture and public perception
Contain words like: Integrity, Diversity, Innovation, Community, Customer Satisfaction, and Sustainability
A statement may follow the descriptive noun.
  “Striving for innovation in all we do.”
  “Promoting diversity & inclusion”
  “We are one team.”
More words are not always better.
  These should be memorable to employees.
  Decisions must reflect values.
Trust and Continuous Development
Leadership, Collaboration, Integrity, Accountability, Passion, Diversity, and Quality
Diversity, Equity, Inclusion, Sustainability
People First, Customer Driven, One Team, Act as Owners, Raise the Bar, Value Different Perspectives
Entrepreneurial Spirit and Employee Focus
Section 13

## Slide 146: Types of Strategic Projects & Portfolios
Business Models
People & Culture
Vision & Mission
Value Proposition
Customer Experience
Technology
Distribution Structure
TRANSFORMATION
Technology
Internal Skills
Mergers & Acquisitions
Operational
Customer Management
Product Development
CAPABILITIES
Market Strategies
Product Strategies
Diversification Strategies
Branding
Innovation
Quality
GROWTH
Section 13

## Slide 147: Business Modeling
Telling the Story
Value Propositions
What problems are being solved by your solution?
Is the solution different and durable?
Customer Segments
Who has the problem, what’s the market size?
Is it measurable and accessible?
Will the solution impact a substantial piece of the market?
Relationship Management
How are relationships conducted?
Email, voice, video technology, face-to-face, seminars, etc.
Frequency of contact
Delivery Channels
How are solutions delivered?
Personal delivery, supply chains, technology delivery, brick & mortar, etc.
Key Activities
Activities performed on a regular basis.
Manufacturing, application development, purchasing, marketing, etc.
Key Resources
People, skills, or competencies required to deliver the solution.
Capital and financial resources
Key Partners
External partners that assist in delivering the solution, or support of the organization.
Can be functional teams that support other functional teams.
Revenue Streams
Where does the financial support come from?
Can be internal and external sources.
Sales, contributions, in-kind donations, reallocation of profits, etc.
Cost Structure
What costs are needed to support the model?
Payroll, 3rd Party costs, technology, capital expenses and overhead, cost of goods, etc.
Section 13

## Slide 148: Detailed and High-Level Models
Different Documents for Same Model but Different Audiences
High-Level: Great for presentations, brief overview of who an organization is, who they support, problems they solve, and how they work.
Detailed: Part of a strategic plan that allows for details too deep for a quick presentation
Note: Every organization may require different elements and formats for approvals / support.
Section 13

## Slide 149: Business Modeling
Designed For: Clarity Execution, LLC
Designed By: Gerald Jeffs
Year: 2025
For-Profit Organizations
  Contract Consulting
Nonprofit Organizations
  Local
  Regional
  State
Educational Providers
  Colleges & Universities
  High School Career Programs
  Professional Organizations
Tools and Applications for Content Development
Networking Applications
Cost of Networking
Unrecoverable Travel
Social Media and Internet Presence
For-Profit Organization Invoicing for Strategy/Project Mgt. Services
Full Training Programs in Strategy/Project Mgt. to Education Providers
Face-to-Face
Video/Mobile Conferencing
Electronic Mail & Text
Turning team and organizational strategies into outcomes that deliver value.
Developing capabilities of people, teams, and organizations in project, portfolio, and strategy management.
Providing Educational Services
Providing Strategy/Project Mgt. Services
Networking with Partners & Market for Services
Development of Tools & Content
Education Providers
  Administrators
  Program Owners
Contracting Firms
  Third-Party Service Providers
Nonprofit Organizations
  Executive Directors
  Board Members
Strategy/Project Mgt. Professional
Social Media Platforms
Tool and Content Development Capabilities
Business Accounting/Finance
Small Business Mgt.
Onsite
Remote/Hybrid
Relationships Mgt.
Value Propositions
Key Activities
Key Partners
Who We Serve
Delivery Methods
Key Resources / Skills
Cost Structure
Revenue Streams

## Slide 150: S.W.O.T. Analysis
Strengths, Weaknesses, Opportunity's, and Threats
Internal Factors
Strengths
Forces unique to the organization
Core competencies Skills, operating capabilities & differentiators
Resources: People & Capital
Weaknesses
Forces limiting an organizations value proposition
Lacking capabilities, skills, capital investments, etc.
Factors that are internal to the organization
The organization has control over these
They can be changed within the organization
External Factors
Opportunities
Forces that can be capitalized
Factors: Political, Economic, Social-Cultural, Technology, Environmental, Legal, etc.
Threats
Forces that can cause disruptions
Factors: Political, Economic, Social-Cultural, Technology, Environmental, Legal, etc.
Factors that are external to the organization
The organization has no control over these
They can’t be changed by the organization
Section 13

## Slide 151: S.W.O.T.’s Done, Now What?
Start Strategic Planning
Opportunities - Strengths (OS)
(Strategies)
What strengths can be used to capitalize on opportunities
Define strategic initiatives by identifying the strength and the opportunity (S1, S3, O4)
Opportunities - Weaknesses (OW)
(Strategies)
What weaknesses if improved can be used to capitalize on opportunities
Define strategic initiatives by identifying the weakness and the opportunity (W2, O1, O3)
Threats - Strengths (TS)
(Strategies)
What strengths can be used to limit a threats impact
Define strategic initiatives by identifying the strength and the threat (S2, T2, T3)
Threats - Weaknesses (TW)
(Strategies)
What weaknesses if improved can be used to limit a threats impact
Define strategic initiatives by identifying the weakness and the threat (W2, W4, T1, T4)
Example
Value of Work: It creates actionable strategies to strengthen a team or organization. A leader should create a draft and then get team input for buy in. Not all initiatives need to be done, pick one or two to start with.
Section 13

## Slide 152: Strengths-Weaknesses-Opportunities-Threats
Strengths
Project Mgt Skills & Credentials
Portfolio Mgt Skills & Credentials
Strategy Mgt Skills & Credentials
Training & Development Skills
Strategy/Project Mgt Content & Tools
Professional Credentials & Documents
Weaknesses
Education Provider Relationships
Nonprofit Ex. Dir. Relationships
3rd Party For-Fee Service Provider Relationships
Network of Decision Makers
Internet Presence
Opportunities
Education Provider Networking Events
Nonprofit Organization Public Events
Professional Organization Networking Events
Internet Platforms
Threats
Demand of For-Fee Contract Services
Demand for Guest Speakers in Strategy/Project Mgt
External Forces
Internal Forces
Opportunities-Strengths (OS)
Strategic Theme(s)
Guest Speaking at Professional Events
  (S1,S2,S3,S4,S5,S6/O1,O2,O3,O4)
Website Creation
  (S5,S6/O4)
Threats-Strengths (TS)
Strategic Theme(s)
Build 3rd Party for Fee Service Provider Relationships
  (S5,S6,T1)
Create Training Content for Education Providers
  (S4,S5,S6/T2)
Opportunities-Weaknesses (OW)
Strategic Theme(s)
Guest Attendance at Professional Networking Events
  (W1,W2,W3,W4/O1,O2,O3)
Website and LinkedIn Business Site
  (W5/O3,O4)
Threats-Weaknesses (TW)
Strategic Theme(s)
Widen Networks of Professionals Decision Makers
  (W1,W2,W3,W4/T1,T2)
Section 13

## Slide 153: Strategic Mapping
Turning Previous Work into a Visual Strategic Plan
Mission, Vision, & Values
These drive all strategies, so they need to be front, and center and alignment must be visible.
S.W.O.T. into
Strategic Themes
A theme will come out of the S.W.O.T. work, there can be as little as one, there shouldn’t be more than four.
Mapping Connections Upward
The categories can change, there should be three to four levels that are connected by a level below, but the below work can jump up more than one level.
Initiatives, Targets, & Measures
Define specific strategic initiatives with targeted objectives, and measurement that present what success looks like
This will be some of the hardest work
Section 13

## Slide 154: Building the Connections Up
Simplicity & Conciseness is King, but Never Easy
The picture will tell the story of a team’s or organization’s direction, what they’re going to do and how they do it. This may appear simple, but that’s only because a lot of work will go into doing it.
Section 13

## Slide 155: Strategic Mapping
Themes
Building Relationships
Speaking Engagements
Internet Presence
Strategic
Objectives
Increase the number of professional decision makers with education providers, 3rd Party For-Fee Service Providers, and Nonprofit Executive Directors.
Increase the frequency of guest speaking engagements with education providers, and professional events.
Creation of internet presence and accessibility to Clarity Execution, LLC.
Delivering Strategic Project Portfolio Management Expertise
Mission
Vision
Make Strategy Management Accessible to People, Teams, and Smaller Organizations
Core Values ∙ Trust ◊ Continuous Development
Strategic Objectives and Strategy Map
Initiatives
Objectives
Measures
Tracking of Engagement by Services Provided
Growth of Engagements in all Services
Track and Report Past Experiences
Increase Access to Decision Makers
Maintain Quality and Current Content
Tracking & Reporting of Network Portfolio
Control Internet Presence, Content, and Access
Engagement Tracking
Case Studies or Testimonials
Engagement of Professional Networks
Website Content 
Build Network Management Capability
Build Website 
Number of People, Teams, & Orgs Supported
Measure Growth until Plateau
Frequency of Content Updates
Number of Accessible Contacts
Web Pages with Informative Content
Incentives
Customer Experience
Improving
Capabilities / Competencies
Professional Networks
Engagement Mgt Tool
Website
Request of For-Fee Services
Increase Engagements
Provides Self Satisfaction
Connections to Services
Opportunity Management
Internet Presence
Understanding of Organization
Professional
Experience




Tracking

Needs Work

Off Track or Not Started




## Slide 156: Branding & Mind Mapping
How We Present Ourselves & How We are Perceived by Others
Branding Matrix
Aligns Core Brand with Values and Culture Internally and Externally.
What’s the organization’s personality and how does it express itself.
What do relationships and market position look like to others.
The competencies in the organization with the offered value proposition.
Mind Mapping
What does an organization want to be in the hearts and minds of people.
How does the organization see itself and how does it present externally?
Mapping can go as deep as needed.
Section 13

## Slide 157: Branding Matrix
How Does the Organization or Team Align Internally & Externally
Usage
Internal & external communications about how the organization defines itself and how it functions; also helps drive what’s being established at the core.
Value Proposition
What problem is being solved & how?
Expression
The way an organization communicates and expresses itself
Vision & Mission
Vision: How does the organization or team accomplish objectives
Mission: What is the core function of the organization or team
Relationships
The nature of relationships with key stakeholders.
Brand Core
What’s the promise and what are the core values that sum up what the brand stands for?
Culture
What are the organization’s or team’s attitude and how do they work & behave?
Competences
What the organization or team are good at, and what makes them better than most?
Position
The market position and what’s in the hearts & minds of key stakeholders?
Personality
What combination of human characteristics or qualities forms the character?
EXTERNAL
INTERNAL
EXTERNAL / INTERNAL
STRATEGY
COMPETITION
INTERACTION
Alignment
There needs to be clear alignment on the diagonal paths (Strategy & Competition), the vertical path (Interaction), and the horizontal path (communications).
COMMUNICATIONS
Section 13

## Slide 158: Branding Matrix
How the Organization Aligns Internally & Externally
Usage
Internal & external communications about how the organization defines itself and how it functions; also helps drive what’s being established at the core.
Value Proposition
Turns Strategy into Beneficial Outcomes
Building Sustainable Competences in Strategic Project Portfolio Management
Expression
Guest Speaking
LinkedIn Content
Website Content
Vision & Mission
Mission: Delivering Strategic Project Portfolio Management Expertise
Vision: Make Strategy Mgt Accessible . . .
Relationships
Personal Focus with Stakeholders
Consistent and Accurate Communications
Brand Core
Strategic Project Portfolio Management Expertise
Culture
Building Trust Based Relationships
Continuously Learning and Improving
Competences
Strategy, Portfolio, and Project Management Expertise
Position
Concierge Level Service
Professional Discipline Service Provider
Educator of Strategic Proj. Portfolio Skills
Personality
Focuses on Mission
Curiosity in Others
Driven to Improve
Community Service
EXTERNAL
INTERNAL
EXTERNAL / INTERNAL
STRATEGY
COMPETITION
INTERACTION
Alignment
There needs to be clear alignment on the diagonal paths (Strategy & Competition), the vertical path (Interaction), and the horizontal path (communications).
COMMUNICATIONS
Section 13

## Slide 159: Hearts & Minds of Others
Example: Clarity Execution
Educator
Customers
Project Management
Strategy Management
Guest Speaker
Courses / Programs
Mentor
Portfolio Management
Business Planning
Strategic Planning
Strategy Execution
Team Development
Tools & Methods
Project Leader
For Profits
Education Providers
Professional Organizations
Nonprofits
Careers in Project Mgt.
Project/Program/Strategy Mgt.
Product Mgt.
Change Mgt. / Changing Culture
Project/Program/Strategy Mgt.
8 to 40 Hours Course Work
Individuals & Teams
Career Development
Mid-Level to Sr. Leaders
Project/Program Prioritization
Resource Management
Schedules, Cost, Risk, Communications
Market Analysis
Solution Viability
Organization Alignment
S.W.O.T. Analysis / Identify Initiatives
Strategic Road Mapping
Organization Socialization
Project & Program Mgt.
Change Management
Stakeholder Mgt.
Applied Project & Program Mgt.
Proj. Portfolio Management
Repository of Tools & Processes
Application of Tools
Standard & Agile Methods
Individuals & Groups
PM Organization Structure
Build Sustainable Org & Teams
Professional Conferences
Project Mgt. Organizations
Under & Graduate Prgms.
Project Mgt. Organizations
H.S. Business Prgms.
Contract Assignments
Remote & Onsite
501c3 / c4 Corps.
Local & Regional
Section 13

## Slide 160: Project Management Careers
Lifelong Learning & Experimenting
It Never Get’s Easier
Section 13

## Slide 161: Industries
All Industries Have Project Managers
International Logistics
Technology
Health Care
Consumer Products
Nonprofit
Construction
Domestic Logistics
Automotive
Legal
Media
Government
Transportation
The Depth of Project Management Changes
Section 13

## Slide 162: Organizational Structure
Where Does Project Management Fit?
Finance
Payables
Receivables
Tax
Payroll
General Accts
Legal
Contracting
Litigation
Compliance
Human Resources
HR Policies
Training
Benefits
Recruiting
Performance
Information
Technology
Applications
Data Storage
Hardware
Security
Integration
Operations
Services
Manufacturing
Supply Chain
Engineering
Safety
Section 13

## Slide 163: Building a Competency
WHY?
In helping people, teams, and organizations Improve, we improve ourselves.
Section 13
LEARN
APPLY KNOWLEDGE
ADJUST /EXPERIENCE
TEACH OTHERS

## Slide 164: Possible Steps
Section 13
Step 2
Step 1
Building the Foundation
Project Coordinator
Experiential Learning
Project Manager
Step 3
Applied Leadership
Sr. Project Manager
Step 4
Balancing Work, Team Development, Strategic Leadership
Portfolio Manager / PMO
Step 5
Strategic Planning & Execution
Strategy Manager / Leader
Step 6
Changing Organizations & Giving Back
C-Level / Educator / Board Member
Complexity of Knowledge & Skills

## Slide 165: Roles, Functions, and Credentials
VP Project-Strategy Management
Dir. Project-Strategy Management
Sr. Project / Portfolio Manager
Sr. Project Manager
Project Coordinator & Project Manager
Organizational Project Portfolios
Project/Strategy Managers Development
Project/Strategy Management Tool-Box
Align Corporate Strategies & PMO
Corporate Project Implementations
Support PM Education & Experiences
Business Unit/Functional Project Portfolios
Operations & Corporate Projects
Project Managers Development
Alignment with Organizational PMO
Creation of Tools & Methodologies
Support PM Education & Experiences
Functional Area Project Portfolio
Operations & Corporate Projects
Creation of Tools & Methodologies
Project Manager(s) Development
Support PM Education & Experiences
Functional & Corporate Projects
Creation of Tools & Methodologies
Support PM Education & Experiences
Internal Functional Projects
Development of PM Skills & Experiences
Support Tracking & Reporting Activities
Advanced Degree & Certifications
Advanced Certifications
Fundamental Courses
Obtaining PMP®
Advanced Certifications
Fundamental Development
Section 13

## Slide 166: Portfolio Management
Operations
Portfolios
Strategic
Portfolios
PRT 1.1
PRJ 1.11
PRJ 1.12
PRJ 1.13
PRT 1.2
PRJ 1.21
PRJ 1.22
PRJ 2.21
PRJ 2.22
PRJ 2.23
PRJ 2.11
PRJ 2.12
PRT 2.1
PRT 2.2
Corporate Portfolio
Resource Allocation
Prioritization
Governance
Tools & Templates
Organization Development
Team Member Development
Methodologies
Financial Management
Section 12

## Slide 167: Needed Skills & Experiences
Communications
Leadership
Project Management
Portfolio Management
Strategy Management
Organizational Development
Industry Specific Knowledge
Product Management
Market Analysis
Cross Cultural Management
Section 13

## Slide 168: A Career of Knowledge & Experience
VP Project-Strategy Management
Dir. Project-Strategy Management
Sr. Project / Portfolio Manager
Sr. Project Manager
Project Coordinator & Project Manager
Highest Level of Industry Knowledge
Highest Organizational Development Skills
Highest Org. Wide Functional Knowledge
10+ Years Project Portfolio Leadership
10+ Years Strategic Portfolio Leadership
10+ Years Leading & Developing Teams
Strong Industry Knowledge
Strong Organizational Development Skills
Strong Functional Area(s) Knowledge
5+ Years Project Portfolio Leadership
5+ Years Strategic Project Portfolio
5+ Years Leading & Developing Teams
Wide Industry Knowledge
Wide Team Development Skills
Wide Functional Area(s) Knowledge
5+ Years Project Management Leadership
5+ Years Leading Strategic Projects
5+ Years Developing People
Good Industry Knowledge
Good Leadership Skills
Good Functional Area Knowledge
Developing Industry Knowledge
Developing People Skills
Developing Functional Area Knowledge
5+ Years Project Management
5+ Years Cross Functional Area Projects
5+ Years Matrix Resource Integration
Industry
Knowledge
Change
Section 13

## Slide 169: Project Management Professional (PMP®)
Requirements
  High school diploma or GED
    60 Months/5 Years Experience within Past 8 Years
  ≥ 4 Year Degree
    36 Months/3 Years Experience within Past 8 Years
  ≥35 hours of project management education/training
  60 Professional Development Units (PDU) every three years
Certification Exam
  180 Questions in 3:50 Hours
  Price: $425 PMI Member/$675 nonmembers
PMP Stats
  Average U.S. Median Salary ≈ $120k
  Current Holders ≈ 1.5m Worldwide
    >500,000 in North America (November 2024)
  Top Countries: U.S., Canada, China
Section 13

## Slide 170: Certified Associate in Project Management (CAPM®)
Requirements
  High school diploma or GED
  No experience requirements
  ≥23 hours of project management education/training
  15 Professional Development Units (PDU) every three years
Certification Exam
  150 Questions in 3:00 Hours
  Price: $225 PMI Member/$300 nonmembers
CAPM Stats
Average U.S. Median Salary ≈ $72k
Current Holders ≈ 1.7m Worldwide
Types of Positions
  Assistant Project Manager
  Project Administrator
  Project Analyst
  Project Coordinator
  Project Manager
  Technical Project Manager
Section 13

## Slide 171: Other Project Management Credentials
https://www.pmi.org
https://www.prince2.com
Section 13
Program Management Professional (PgMP®)
Portfolio Management Professional (PfMP®)
PMI Professional in Business Analysis (PMI-PBA®)
PMI Risk Management Professional (PMI-RMP®)
PMI Scheduling Professional (PMI-SP®)
Prince2 Foundation
Prince2 Practitioner
Prince2 Agile Foundation
Prince2 Agile Practitioner
PMI Agile Certified Practitioner (PMI-ACP®)
Disciplined Agile Scrum Master (DASM®)
Disciplined Agile Senior Scrum Master (DASSM®)
Undergraduate, Graduate, or University Certifications/Degrees

## Slide 172: Thank You
Gerald Jeffs
clarityexecution.com
www.linkedin.com/in/gerryjeffs
jeffsgerry@gmail.com
925-487-5982
Tracy, CA

## Slide 173
Excel File &
MS Project Format
Tool Chest

## Slide 174: Value Iteration/Sprint Management
Prioritized Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Resources Needed
Resources
Resources
Resources
Expected Outcome
Outcome
Outcome
Outcome
#
1
2
3
Service/Area
Service/Area
Service/Area
Service/Area
Pipeline/Backlog of Iterations/Sprints
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint
Iteration/Sprint

## Slide 175: Status Report Template
Report Date: TBD
Project: TBD
Project Manager
TBD
Tech Project Manager
TBD
Tracking
Challenges
Critical
Status Indicators
Holding
Improved
Decreased
Tracking Direction
Project Status
Comp:
00%
Resources:
Schedule:
Scope:
Risks:
Cost:
Key Milestones / Key Schedule Dates
Milestone
Planned Date
Status
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
TBD
TBD
0%
Challenge / Issue / Actions
Resolve Date
Status
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
Support Needed / Decision to be Made
From / Owner
Status
Scope Approval Authorities – Who?
Exec Sponsors
Pending
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD

## Slide 176: Strengths-Weaknesses-Opportunities-Threats
Strengths
TBD
Weaknesses
TBD
Opportunities
TBD
Threats
TBD
External Forces
Internal Forces
Opportunities-Strengths (OS)
Strategic Theme(s)
TBD
Threats-Strengths (TS)
Strategic Theme(s)
TBD
Opportunities-Weaknesses (OW)
Strategic Theme(s)
TBD
Threats-Weaknesses (TW)
Strategic Theme(s)
TBD

## Slide 177: Business Modeling
Designed For: TBD
Designed By: TBD
Year: TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
Relationships Mgt.
Value Propositions
Key Activities
Key Partners
Who We Serve
Delivery Methods
Key Resources / Skills
Cost Structure
Revenue Streams

## Slide 178: Strategic Mapping
Themes
Highest Level Description
Highest Level Description
Highest Level Description
Strategic
Objectives
End outcomes from successfully executing the strategy.
End outcomes from successfully executing the strategy.
End outcomes from successfully executing the strategy.
Looks forward and creates a mental image of the ideal state that the organization wishes to achieve.
Mission
Vision
Concise explanation of the organization's reason for existence. It describes the organization's purpose and its overall intention.
Core Values ∙ The beliefs & principals that articulate culture
Strategic Objectives and Strategy Map
Initiatives
Objectives
Measures
Indicators of progress towards a desirable outcome.
Intended Results
Intended Results
Intended Results
Intended Results
Expected Outcomes
Expected Outcomes
Expected Outcomes
End outcomes from successfully executing the strategy.
Indicators of progress towards a desirable outcome.
Indicators of progress towards a desirable outcome.
Indicators of progress towards a desirable outcome.
Financial
Customer Experience
Improving
Capabilities / Competencies
Action
Action
Action
Strategic Objective
Strategic Objective
Strategic Objective
Strategic Objective
Strategic Objective
Strategic Objective
Strategic Objective
Strategic Objective

## Slide 179: Hearts & Minds of Others
INSERT LOGO
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD

## Slide 180: Branding
Usage
Internal & external communications about how the organization defines itself and how it functions; also helps drive what’s being established at the core.
Value Proposition
What problem is being solved & how?
Expression
The way an organization communicates and expresses itself
Vision & Mission
Vision: How does the organization or team accomplish objectives
Mission: What is the core function of the organization or team
Relationships
The nature of relationships with key stakeholders.
Brand Core
What’s the promise and what are the core values that sum up what the brand stands for?
Culture
What are the organization’s or team’s attitude and how do they work & behave?
Competences
What the organization or team are good at, and what makes them better than most?
Position
The market position and what’s in the hearts & minds of key stakeholders?
Personality
What combination of human characteristics or qualities forms the character?
EXTERNAL
INTERNAL
EXTERNAL / INTERNAL
STRATEGY
COMPETITION
INTERACTION
Alignment
There needs to be clear alignment on the diagonal paths (Strategy & Competition), the vertical path (Interaction), and the horizontal path (communications).
COMMUNICATIONS